## Welding
Shedgum Gas Plant Metals Unit Weldig Shop Activity Q1
# | Welder Name | Nationality | Welder Status | Welder Symble | Area | Work location | Date | Welding process | Welding test supplement | Welding joint | Material type | Work Ordre | RFI | WPS | Dia | Type of test | PMI | PWHT | Result | inspection
1 | Altammar,Ali |  |  | ADHBA | Utility | K-102 C | 2025-01-01 | GTAW | S07 | SW#1 | SS |  |  | P1-11 | 8" | X-ray | Yes | N/A | Pass
2 | Altammar,Ali |  |  | ADHBA | Utility | K-102 C | 2025-01-01 | GTAW | S07 | SW#2 | SS |  |  | P1-11 | 8" | X-ray | Yes | N/A | Pass
3 | Alonyzi,Fahad |  |  | ADHHL | Utility | K-102 C | 2025-01-02 | GTAW | S07 | SW#3 | SS |  |  | P1-11 | 6" | X-ray | Yes | N/A | Pass
4 | Alonyzi,Fahad | Saudi | Active | ADHHL | Utility | K-102 C | 2025-01-02 | GTAW | S07 | SW#4 | SS |  |  | P1-11 | 6" | X-ray | Yes | N/A | Pass
5 | Alkalaf,Abdulrahim | Saudi | Active | ADGXD | Utility | K-102 C | 2025-01-03 | GTAW | S07 | SW#5 | SS |  |  | P1-11 | 6" | X-ray | Yes | N/A | Pass
6 | Alkalaf,Abdulrahim |  |  | ADGXD | Utility | K-102 C | 2025-01-03 | GTAW | S07 | SW#6 | SS |  |  | P1-11 | 6" | X-ray | Yes | N/A | Pass
7 | Altammar,Ali | Saudi | Active | ADHBA | Utility | K-102 C | 2025-01-04 | GTAW | S07 | SW#7 | SS |  |  | P1-11 | 4" | X-ray | Yes | N/A | Pass
8 | Alonyzi,Fahad |  |  | ADHHL | Utility | K-102 C | 2025-01-04 | GTAW | S07 | SW#8 | SS |  |  | P1-11 | 4" | X-ray | Yes | N/A | Pass
9 | Altammar,Ali |  |  | ADHBA | Utility | K-102 C | 2025-01-05 | GTAW | S07 | SW#9 | SS |  |  | P1-11 | 4" | X-ray | Yes | N/A | Pass
10 | Altammar,Ali |  |  | ADHBA | Utility | K-102 C | 2025-01-05 | GTAW | S07 | SW#10 | SS |  |  | P1-11 | 4" | X-ray | Yes | N/A | Pass
11 | Alonyzi,Fahad |  |  | ADHHL | Utility | K-102 C | 2025-01-06 | GTAW | S07 | SW#11 | SS |  |  | P1-11 | 4" | X-ray | Yes | N/A | Pass
12 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#1 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
13 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#2 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
14 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#3 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
15 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#4 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
16 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#5 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
17 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#6 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
18 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#7 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
19 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#8 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
20 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#9 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
21 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#10 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
22 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#11 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
23 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#12 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
24 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#13 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
25 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A Norht | 2025-01-07 | GTAW | S07 | SW#14 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
26 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#1 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
27 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#2 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
28 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#3 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
29 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#4 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
30 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#5 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
31 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#6 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
32 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#7 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
33 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#8 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
34 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#9 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
35 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#10 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
36 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#11 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
37 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#12 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
38 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#13 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
39 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#14 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
40 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#15 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
41 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#16 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
42 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#17 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
43 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#18 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
44 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#19 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
45 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#20 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
46 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#21 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
47 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-08 | GTAW | S07 | SW#22 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
48 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 B South | 2025-01-09 | GTAW | S07 | SW#1 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
49 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#2 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
50 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#3 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
51 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#4 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
52 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#5 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
53 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#6 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
54 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#7 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
55 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#8 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
56 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#9 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
57 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#10 | Cs |  |  | P1-11 | 1" | PT | N/A | Yes | Pass
58 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#11 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
59 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#12 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
60 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#13 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
61 | Altammar,Ali |  |  | ADHBA | GT#2 | D-201 A South | 2025-01-09 | GTAW | S07 | SW#14 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
62 | Gonzago,Jayson |  |  | ADHXC | Inlet | PZV 119 B | 2025-01-11 | SMAW | S01 | SW#1 | CS |  |  | P1-1 | 6" | PT | N/A | N/A | Pass
63 | Alaqil,Abdullah |  |  | XYVI | Inlet | PZV 119 B | 2025-01-11 | SMAW | S01 | SW#2 | CS |  |  | P1-1 | 6" | PT | N/A | N/A | Pass
64 | Alaqil,Abdullah |  |  | XYVI | Inlet | PZV 119 B | 2025-01-12 | SMAW | S01 | SW#3 | CS |  |  | P1-1 | 6" | PT | N/A | N/A | Pass
65 | Alaqil,Abdullah |  |  | XYVI | Inlet | PZV 119 B | 2025-01-12 | SMAW | S01 | SW#4 | CS |  |  | P1-1 | 4" | PT | N/A | N/A | Pass
66 | Alaqil,Abdullah |  |  | XYVI | Inlet | PZV 119 B | 2025-01-13 | SMAW | S01 | SW#5 | CS |  |  | P1-1 | 4" | PT | N/A | N/A | Pass
67 | Alaqil,Abdullah | Saudi | Active | XYVI | Inlet | PZV 119 B | 2025-01-13 | SMAW | S01 | SW#6 | CS |  |  | P1-1 | 1" | PT | N/A | N/A | Pass
68 | Alhassan,Abdullah | Saudi | Active | XYYB | Inlet | PZV 119 B | 2025-01-13 | SMAW | S01 | SW#7 | CS |  |  | P1-1 | 1" | PT | N/A | N/A | Pass
69 | Alhassan,Abdullah |  |  | XYYB | Inlet | PZV 119 B | 2025-01-13 | SMAW | S01 | SW#8 | CS |  |  | P1-1 | 1" | PT | N/A | N/A | Pass
70 | Alhassan,Abdullah |  |  | XYYB | Inlet | PZV 119 B | 2025-01-13 | SMAW | S01 | SW#9 | CS |  |  | P1-1 | 1" | PT | N/A | N/A | Pass
71 | Gonzago,Jayson | Non-Saudi | Active | ADHXC | POSH | Pouring Arm#8 | 2025-01-13 | SMAW | S01 | SW#1 | CS |  |  | P1-1 | 4" | PT | N/A | N/A | Pass
72 | Alaqil,Abdullah |  |  | XYVI | POSH | Pouring Arm#8 | 2025-01-13 | SMAW | S01 | SW#2 | CS |  |  | P1-1 | 4" | PT | N/A | N/A | Pass
73 | Alaqil,Abdullah |  |  | XYVI | POSH | Pouring Arm#8 | 2025-01-13 | SMAW | S01 | SW#3 | CS |  |  | P1-1 | 4" | PT | N/A | N/A | Pass
74 | Alhassan,Abdullah |  |  | XYYB | POSH | Pouring Arm#8 | 2025-01-13 | SMAW | S01 | SW#4 | CS |  |  | P1-1 | 4" | PT | N/A | N/A | Pass
75 | Alonyzi,Fahad |  |  | ADHHL | FGC | PZV 114 A | 2025-01-14 | GTAW | S07 | SW#1 | CS |  |  | P1-11 | 1" | PT | N/A | N/A | Pass
76 | Alonyzi,Fahad |  |  | ADHHL | FGC | PZV 114 B | 2025-01-14 | GTAW | S07 | SW#2 | CS |  |  | P1-11 | 1" | PT | N/A | N/A | Pass
77 | Alonyzi,Fahad |  |  | ADHHL | FGC | PZV 114 C | 2025-01-14 | GTAW | S07 | SW#3 | CS |  |  | P1-11 | 1" | PT | N/A | N/A | Pass
78 | Alaqil,Abdullah |  |  | XYVI | GT#2 | D-203 Reflex Drum | 2025-01-15 | SMAW | S01 | SW#1 | CS |  |  | P1-1 | 4" | X-ray | N/A | Yes | Pass
79 | Alaqil,Abdullah |  |  | XYVI | GT#2 | D-203 Reflex Drum | 2025-01-16 | SMAW | S01 | SW#2 | CS |  |  | P1-1 | 4" | X-ray | N/A | Yes | Pass
80 | Alaqil,Abdullah |  |  | XYVI | GT#2 | D-203 Reflex Drum | 2025-01-16 | SMAW | S01 | SW#3 | CS |  |  | P1-1 | 1" | X-ray | N/A | Yes | Pass
81 | Alaqil,Abdullah |  |  | XYVI | GT#2 | D-203 Reflex Drum | 2025-01-17 | SMAW | S01 | SW#4 | CS |  |  | P1-1 | 1" | X-ray | N/A | Yes | Pass
82 | Alabood,Ahmed | Saudi | Active | BAACX | GT#2 | D-202 Flash Drum | 2025-01-17 | SMAW | S01 | SW#1 | CS |  |  | P1-1 | 4" | X-ray | N/A | Yes | Pass
83 | Alaqil,Abdullah |  |  | XYVI | GT#2 | D-202 Flash Drum | 2025-01-17 | SMAW | S01 | SW#2 | CS |  |  | P1-1 | 4" | X-ray | N/A | Yes | Pass
84 | Alzayid, Meshal | Saudi | Active | BAACC | GT#2 | D-202 Flash Drum | 2025-01-17 | SMAW | S01 | SW#3 | CS |  |  | P1-1 | 4" | X-ray | N/A | Yes | Pass
85 | Alaqil,Abdullah |  |  | XYVI | GT#2 | D-202 Flash Drum | 2025-01-17 | SMAW | S01 | SW#4 | CS |  |  | P1-1 | 4" | X-ray | N/A | Yes | Pass
86 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-17 | GTAW | S07 | SW#5 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
87 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-17 | GTAW | S07 | SW#5 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Fail
88 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-18 | GTAW | S07 | SW#6 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
89 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-202 Flash Drum | 2025-01-18 | GTAW | S07 | SW#7 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
90 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | D-202 Flash Drum | 2025-01-18 | GTAW | S07 | SW#8 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
91 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-18 | GTAW | S07 | SW#9 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
92 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-18 | GTAW | S07 | SW#10 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
93 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-18 | GTAW | S07 | SW#11 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
94 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-18 | GTAW | S07 | SW#12 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
95 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#13 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
96 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#14 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
97 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#15 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
98 | Ansari,Naiz | Non-Saudi | Active | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#16 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
99 | Bhadoor,Rajesh | Non-Saudi | Active | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#17 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
100 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#18 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
101 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#19 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
102 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#20 | Cs |  |  | P1-11 | 1 1/2" | PT | N/A | Yes | Pass
103 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#21 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
104 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#22 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
105 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#23 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
106 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#24 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
107 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#25 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
108 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#26 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
109 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#27 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
110 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#28 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
111 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#29 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
112 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#30 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
113 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#31 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
114 | Altammar,Ali |  |  | ADHBA | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#32 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
115 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#33 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
116 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#34 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
117 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-19 | GTAW | S07 | SW#35 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
118 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#36 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
119 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#37 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
120 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#38 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
121 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#39 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
122 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#40 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
123 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#41 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
124 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#42 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
125 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#43 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
126 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#44 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
127 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#45 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
128 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#46 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
129 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#47 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
130 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#48 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
131 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#49 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
132 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#50 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
133 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#51 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
134 | Alonyzi,Fahad |  |  | ADHHL | GT#2 | D-202 Flash Drum | 2025-01-20 | GTAW | S07 | SW#52 | Cs |  |  | P1-11 | 3/4" | PT | N/A | Yes | Pass
135 | Alonyzi,Fahad |  |  | ADHHL | Inlet | GM931 | 2025-01-21 | GTAW | S07 | FW#1 | Cs |  | 70389171 | P1-11 | 3/4" | PT | Yes | N/A | Pass
136 | Alonyzi,Fahad |  |  | ADHHL | Inlet | GM931 | 2025-01-21 | GTAW | S07 | FW#2 | Cs |  | 70389171 | P1-11 | 3/4" | PT | Yes | N/A | Pass
137 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | Skimmer Line | 2025-01-21 | GTAW | S07 | SW#1 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
138 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | Skimmer Line | 2025-01-21 | GTAW | S07 | SW#2 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
139 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | Skimmer Line | 2025-01-21 | GTAW | S07 | SW#3 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
140 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | Skimmer Line | 2025-01-22 | GTAW | S07 | SW#4 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
141 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | Skimmer Line | 2025-01-22 | GTAW | S07 | SW#5 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
142 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | Skimmer Line | 2025-01-22 | GTAW | S07 | SW#6 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
143 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | Skimmer Line | 2025-01-23 | GTAW | S07 | SW#7 | Cs |  |  | P1-11 | 2" | X-ray | N/A | Yes | Pass
144 | Alkalaf,Abdulrahim |  |  | ADGXD | GT#2 | Skimmer Line | 2025-01-23 | GTAW | S07 | SW#8 | Cs |  |  | P1-11 | 3" | X-ray | N/A | Yes | Pass
يمثل هذا الشكل مقسم طريقة عرض جدول. لا يتوفر الدعم لمقسم طريقة عرض الجداول في هذا الإصدار من Excel. إذا تم تعديل الشكل في إصدار سابق من Excel أو إذا تم حفظ المصنف في Excel 2007 أو إصدار سابق، فسيتعذر استخدام مقسم طريقة عرض الجدول.
يمثل هذا الشكل مقسم طريقة عرض جدول. لا يتوفر الدعم لمقسم طريقة عرض الجداول في هذا الإصدار من Excel. إذا تم تعديل الشكل في إصدار سابق من Excel أو إذا تم حفظ المصنف في Excel 2007 أو إصدار سابق، فسيتعذر استخدام مقسم طريقة عرض الجدول.
يمثل هذا الشكل مقسم طريقة عرض جدول. لا يتوفر الدعم لمقسم طريقة عرض الجداول في هذا الإصدار من Excel. إذا تم تعديل الشكل في إصدار سابق من Excel أو إذا تم حفظ المصنف في Excel 2007 أو إصدار سابق، فسيتعذر استخدام مقسم طريقة عرض الجدول.
يمثل هذا الشكل مقسم طريقة عرض جدول. لا يتوفر الدعم لمقسم طريقة عرض الجداول في هذا الإصدار من Excel. إذا تم تعديل الشكل في إصدار سابق من Excel أو إذا تم حفظ المصنف في Excel 2007 أو إصدار سابق، فسيتعذر استخدام مقسم طريقة عرض الجدول.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Hydrotest.
Shedgum Gas Plant Metals Unit Hydrotest Report
# | Area | Work location | Date | test prassure | Material type | Work Ordre | Dia | Results | inspection | PWHT
1 | GT#3 | FCV 106 C | 2025-01-13 | 1100 | CS |  | 6" * 10" | Shop | Manoharan, Rajesh | No
2 | GT#3 | GM-303 | 2025-01-14 | 1100 | CS |  | 8" | Shop | Manoharan, Rajesh | No
3 | GT#3 | GM-303 | 2025-01-14 | 1100 | CS |  | 8" | Shop | Manoharan, Rajesh | No
4 | Inlet | PZV 119 | 2025-01-16 | 1100 | CS |  | 6" | Shop | Manoharan, Rajesh | No
5 | Inlet | PZV 119 | 2025-01-16 | 1100 | CS |  | 4" | Shop | Manoharan, Rajesh | No
6 | FGC | PZV 114 A | 01/20/2025 | 1100 | CS |  | 8" | Shop | Manoharan, Rajesh | No
7 | FGC | PZV 114 B | 01/20/2025 | 1100 | CS |  | 8" | Shop | Manoharan, Rajesh | No
8 | FGC | PZV 114 C | 01/20/2025 | 1100 | CS |  | 8" | Shop | Manoharan, Rajesh | No

## Equipment's
Shedgum Gas Plant Metals Unit Shop Equipment's
Equipment’s | Equipment Type | SR. Number | inspection | Next inspection | Remaining on inspection | Condition | Remark
Fixed Welding machine #1 | Fixed Welding Machine | LA-275248 | 2024-08-05 | 2023-01-14 | -745 | Not work | Not work
Fixed Welding machine #2 | Fixed Welding Machine | LA-275248 | 2024-08-05 | 2025-02-04 | 7 | Good
Fixed Welding machine #3 | Fixed Welding Machine | LA-275248 | 2024-08-05 | 2025-02-04 | 7 | Good
Fixed Welding machine #4 | Fixed Welding Machine | LA-275248 | 2023-08-15 | 2023-01-01 | -758 | Not work | Not work
Fixed Welding machine #5 | Fixed Welding Machine | LA-275248 | 2024-08-05 | 2025-02-04 | 7 | Good
Fixed Welding machine #6 | Fixed Welding Machine | LA-275248 | 2024-08-05 | 2025-02-04 | 7 | Good
Fixed Welding machine #7 | Fixed Welding Machine | LA-275248 | 2023-08-15 | 2023-02-14 | -714 | Not work | Not work
Fixed Welding machine #8 | Fixed Welding Machine | LA-275248 | 2023-08-15 | 2023-11-28 | -427 | Not work | Not work
Welding machine#2 | Welding Machine | MK-020025C | 2024-08-05 | 2025-02-04 | 7 | Good
Welding machine#3 | Welding Machine | MK-020004C | 2024-08-05 | 2025-02-04 | 7 | Good
Welding machine#4 | Welding Machine | MG-500059C | 2024-08-05 | 2025-02-04 | 7 | Not work | Not work- missing cable
Welding machine ESAB# 1 | Portable Welding | 7473267683 | 2024-08-05 | 2025-02-04 | 7 | Good
Welding machine ESAB# 2 | Portable Welding | 7473267682 | 2024-08-05 | 2025-02-04 | 7 | Good
Welding machine ESAB# 3 | Portable Welding | 2393265818 | 2024-08-05 | 2025-02-04 | 7 | Good
Welding machine ESAB# 4 | Portable Welding | 2393265817 | 2024-08-05 | 2025-02-04 | 7 | Good
Plasma cutter | Plasma | 1250-009144 | 2024-08-05 | 2025-02-04 | 7 | Good
Electrode Oven CS | Electrode Oven | 10031368-1 | 2024-08-05 | 2025-02-04 | 7 | Good
Electrode Oven SS | Electrode Oven | 50022008 | 2024-08-05 | 2025-02-04 | 7 | Good
Portable Electrode Oven #1 | Electrode Oven | 512201327674 | 2024-08-05 | 2025-02-04 | 7 | Good
Portable Electrode Oven #2 | Electrode Oven | 1116159 | 2024-08-05 | 2025-02-04 | 7 | Good
Portable Electrode Oven #3 | Electrode Oven | 1519598 | 2024-08-05 | 2025-02-04 | 7 | Good
Portable Electrode Oven #4 | Electrode Oven | 1519599 | 2024-08-05 | 2025-02-04 | 7 | Good
Formulas:
Remaining on inspection = Equipments[[#This Row],[Next inspection]]-TODAY()

## Full Time
Shedgum Gas Plant Metals Unit Full Time Equipment's
Equipment Description | Equipment Number | Equipment Type | Condition | Location | Meter Reading | Unit | Next PM Service Due | Hour | Remarks
AC Machine, Diesel 20t | 43R000049 | A/C | Good | Main substation | 0 | Hour | 2025-02-18 | 0
AC Machine, Diesel 20t | 43R000053 | A/C | Good | Utility | 0 | Hour | 2025-02-18 | 0
Air Compressor, Diesel, 22CMM | 05R008254 | Air compresor | Good | Utility | 0 | Hour | 2025-02-18 | 0
Floodlight & Generator 6-8KW | 24R004297 | Flood light | Good | FGC | 0 | Hour | 2025-02-18 | 0
Floodlight & Generator 6-8KW | 24R004256 | Flood light | Good | Sulfur Handling Parking | 0 | Meter | 2025-02-18 | 0
Forklift, Diesel 2.5t | 89R002835 | Forklift | Good | Metals Shop Parking | 0 | Meter | 2024-01-19 | 200
Forklift, Diesel 2.5t | 89R002836 | Forklift | Needs repair | Metals Shop Parking | 0 | Hour | 2024-04-29 | 3948
Forklift, Diesel, 7 tone | 89R005619 | Forklift | Good | Metals Shop Parking | 7040 | Meter | 2025-04-05 | 7288
Manlift, Articulated 18M | 58107331 | Manlift | Good | Metals Shop Parking | 0 | Hour | 2025-02-18 | 0
Manlift, Articulated 24M | 58R000018 | Manlift | Good | Sulfur Handling Parking | 510 | Hour | 2025-02-18 | 805
Manlift | 58R002003 | Manlift | Good | Metals Shop Parking | 30 | Hour | 2025-02-18 | 150
Welding Machine, Diesel 400A | 06R007318 | Welding machine | Good | FGC | 0 | Hour | 2024-04-16 | 2760
Welding Machine, Diesel 400A | 06R007483 | Welding machine | Not work | SRU | 1373 | Hour | 2024-03-07 | 1400
Welding Machine, Diesel 400A | 06R007485 | Welding machine | Good | HP | 564 | Hour | 2025-02-27 | 748
Welding Machine, Diesel 400A | 06R007489 | Welding machine | Good | HP | 1451 | Hour | 2025-02-13 | 1488
Welding Machine, Diesel 400A | 06R007314 | Welding machine | Good | SRU | 826 | Hour | 2025-03-01 | 1117

## SABA.
Shedgum Gas Plant Metals Unit SABA Trailers
Date | Week | Equipment No. | Check List Item | Condition | Remark
2025-01-01 | Week 1 | #1 FA-151782 | Breathing regulator | Good | working good
2025-01-01 | Week 1 | #1 FA-151782 | 3- Harnesses Straps | Good | working good
2025-01-01 | Week 1 | #1 FA-151782 | 6- Cylinder Full/Empty | Good | working good
2025-01-01 | Week 1 | #1 FA-151782 | 3- SKA-PAK Cylinder | Good | working good
2025-01-01 | Week 1 | #1 FA-151782 | Valve | Good | working good
2025-01-01 | Week 1 | #1 FA-151782 | Cylinder Pressure Gauge | Good | working good
2025-01-01 | Week 1 | #1 FA-151782 | 3- Face piece | Good | working good
2025-01-01 | Week 1 | #1 FA-151782 | Hook | Good | working good
2025-01-01 | Week 1 | #1 FA-151782 | Leg Support | Good | working good
2025-01-01 | Week 1 | #1 FA-151782 | Tire | Good | working good
2025-01-01 | Week 1 | #1 FA-151782 | Hydrotest Date | Good | working good
2025-01-01 | Week 1 | #2 FA-151782 | Breathing regulator | Not Available | The equipment operates with high efficiency.
2025-01-01 | Week 1 | #2 FA-151782 | 3- Harnesses Straps | Not Available | Under repair
2025-01-01 | Week 1 | #2 FA-151782 | 6- Cylinder Full/Empty | Not Available | Under repair
2025-01-01 | Week 1 | #2 FA-151782 | 3- SKA-PAK Cylinder | Not Available | Under repair
2025-01-01 | Week 1 | #2 FA-151782 | Valve | Not Available | Under repair
2025-01-01 | Week 1 | #2 FA-151782 | Cylinder Pressure Gauge | Not Available | Under repair
2025-01-01 | Week 1 | #2 FA-151782 | 3- Face piece | Not Available | Under repair
2025-01-01 | Week 1 | #2 FA-151782 | Hook | Not Available | Under repair
2025-01-01 | Week 1 | #2 FA-151782 | Leg Support | Not Available | Under repair
2025-01-01 | Week 1 | #2 FA-151782 | Tire | Not Available | Under repair
2025-01-01 | Week 1 | #2 FA-151782 | Hydrotest Date | Not Available | Under repair
2025-01-01 | Week 1 | #3 FA-151782 | Breathing regulator | Good | working good
2025-01-01 | Week 1 | #3 FA-151782 | 3- Harnesses Straps | Good | working good
2025-01-01 | Week 1 | #3 FA-151782 | 6- Cylinder Full/Empty | Good | working good
2025-01-01 | Week 1 | #3 FA-151782 | 3- SKA-PAK Cylinder | Good | working good
2025-01-01 | Week 1 | #3 FA-151782 | Valve | Good | working good
2025-01-01 | Week 1 | #3 FA-151782 | Cylinder Pressure Gauge | Good | working good
2025-01-01 | Week 1 | #3 FA-151782 | 3- Face piece | Good | working good
2025-01-01 | Week 1 | #3 FA-151782 | Hook | Good | working good
2025-01-01 | Week 1 | #3 FA-151782 | Leg Support | Good | working good
2025-01-01 | Week 1 | #3 FA-151782 | Tirep | Good | working good
2025-01-01 | Week 1 | #3 FA-151782 | Hydrotest Date | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | Breathing regulator | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | 3- Harnesses Straps | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | 6- Cylinder Full/Empty | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | 3- SKA-PAK Cylinder | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | Valve | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | Cylinder Pressure Gauge | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | 3- Face piece | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | Hook | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | Leg Support | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | Tire | Good | working good
2025-01-08 | Week 2 | #1 FA-151782 | Hydrotest Date | Good | working good
2025-01-08 | Week 2 | #2 FA-151782 | Breathing regulator | Not Available | The equipment operates with high efficiency.
2025-01-08 | Week 2 | #2 FA-151782 | 3- Harnesses Straps | Not Available | Under repair
2025-01-08 | Week 2 | #2 FA-151782 | 6- Cylinder Full/Empty | Not Available | Under repair
2025-01-08 | Week 2 | #2 FA-151782 | 3- SKA-PAK Cylinder | Not Available | Under repair
2025-01-08 | Week 2 | #2 FA-151782 | Valve | Not Available | Under repair
2025-01-08 | Week 2 | #2 FA-151782 | Cylinder Pressure Gauge | Not Available | Under repair
2025-01-08 | Week 2 | #2 FA-151782 | 3- Face piece | Not Available | Under repair
2025-01-08 | Week 2 | #2 FA-151782 | Hook | Not Available | Under repair
2025-01-08 | Week 2 | #2 FA-151782 | Leg Support | Not Available | Under repair
2025-01-08 | Week 2 | #2 FA-151782 | Tire | Not Available | Under repair
2025-01-08 | Week 2 | #2 FA-151782 | Hydrotest Date | Not Available | Under repair
2025-01-08 | Week 2 | #3 FA-151782 | Breathing regulator | Good | working good
2025-01-08 | Week 2 | #3 FA-151782 | 3- Harnesses Straps | Good | working good
2025-01-08 | Week 2 | #3 FA-151782 | 6- Cylinder Full/Empty | Good | working good
2025-01-08 | Week 2 | #3 FA-151782 | 3- SKA-PAK Cylinder | Good | working good
2025-01-08 | Week 2 | #3 FA-151782 | Valve | Good | working good
2025-01-08 | Week 2 | #3 FA-151782 | Cylinder Pressure Gauge | Good | working good
2025-01-08 | Week 2 | #3 FA-151782 | 3- Face piece | Good | working good
2025-01-08 | Week 2 | #3 FA-151782 | Hook | Good | working good
2025-01-08 | Week 2 | #3 FA-151782 | Leg Support | Good | working good
2025-01-08 | Week 2 | #3 FA-151782 | Tirep | Good | working good
2025-01-08 | Week 2 | #3 FA-151782 | Hydrotest Date | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | Breathing regulator | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | 3- Harnesses Straps | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | 6- Cylinder Full/Empty | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | 3- SKA-PAK Cylinder | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | Valve | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | Cylinder Pressure Gauge | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | 3- Face piece | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | Hook | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | Leg Support | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | Tire | Good | working good
2025-01-15 | Week 3 | #1 FA-151782 | Hydrotest Date | Good | working good
2025-01-15 | Week 3 | #2 FA-151782 | Breathing regulator | Not Available | The equipment operates with high efficiency.
2025-01-15 | Week 3 | #2 FA-151782 | 3- Harnesses Straps | Not Available | Under repair
2025-01-15 | Week 3 | #2 FA-151782 | 6- Cylinder Full/Empty | Not Available | Under repair
2025-01-15 | Week 3 | #2 FA-151782 | 3- SKA-PAK Cylinder | Not Available | Under repair
2025-01-15 | Week 3 | #2 FA-151782 | Valve | Not Available | Under repair
2025-01-15 | Week 3 | #2 FA-151782 | Cylinder Pressure Gauge | Not Available | Under repair
2025-01-15 | Week 3 | #2 FA-151782 | 3- Face piece | Not Available | Under repair
2025-01-15 | Week 3 | #2 FA-151782 | Hook | Not Available | Under repair
2025-01-15 | Week 3 | #2 FA-151782 | Leg Support | Not Available | Under repair
2025-01-15 | Week 3 | #2 FA-151782 | Tire | Not Available | Under repair
2025-01-15 | Week 3 | #2 FA-151782 | Hydrotest Date | Not Available | Under repair
2025-01-15 | Week 3 | #3 FA-151782 | Breathing regulator | Good | working good
2025-01-15 | Week 3 | #3 FA-151782 | 3- Harnesses Straps | Good | working good
2025-01-15 | Week 3 | #3 FA-151782 | 6- Cylinder Full/Empty | Good | working good
2025-01-15 | Week 3 | #3 FA-151782 | 3- SKA-PAK Cylinder | Good | working good
2025-01-15 | Week 3 | #3 FA-151782 | Valve | Good | working good
2025-01-15 | Week 3 | #3 FA-151782 | Cylinder Pressure Gauge | Good | working good
2025-01-15 | Week 3 | #3 FA-151782 | 3- Face piece | Good | working good
2025-01-15 | Week 3 | #3 FA-151782 | Hook | Good | working good
2025-01-15 | Week 3 | #3 FA-151782 | Leg Support | Good | working good
2025-01-15 | Week 3 | #3 FA-151782 | Tirep | Good | working good
2025-01-15 | Week 3 | #3 FA-151782 | Hydrotest Date | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | Breathing regulator | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | 3- Harnesses Straps | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | 6- Cylinder Full/Empty | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | 3- SKA-PAK Cylinder | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | Valve | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | Cylinder Pressure Gauge | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | 3- Face piece | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | Hook | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | Leg Support | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | Tire | Good | working good
2025-01-22 | Week 4 | #1 FA-151782 | Hydrotest Date | Good | working good
2025-01-22 | Week 4 | #2 FA-151782 | Breathing regulator | Not Available | The equipment operates with high efficiency.
2025-01-22 | Week 4 | #2 FA-151782 | 3- Harnesses Straps | Not Available | Under repair
2025-01-22 | Week 4 | #2 FA-151782 | 6- Cylinder Full/Empty | Not Available | Under repair
2025-01-22 | Week 4 | #2 FA-151782 | 3- SKA-PAK Cylinder | Not Available | Under repair
2025-01-22 | Week 4 | #2 FA-151782 | Valve | Not Available | Under repair
2025-01-22 | Week 4 | #2 FA-151782 | Cylinder Pressure Gauge | Not Available | Under repair
2025-01-22 | Week 4 | #2 FA-151782 | 3- Face piece | Not Available | Under repair
2025-01-22 | Week 4 | #2 FA-151782 | Hook | Not Available | Under repair
2025-01-22 | Week 4 | #2 FA-151782 | Leg Support | Not Available | Under repair
2025-01-22 | Week 4 | #2 FA-151782 | Tire | Not Available | Under repair
2025-01-22 | Week 4 | #2 FA-151782 | Hydrotest Date | Not Available | Under repair
2025-01-22 | Week 4 | #3 FA-151782 | Breathing regulator | Good | working good
2025-01-22 | Week 4 | #3 FA-151782 | 3- Harnesses Straps | Good | working good
2025-01-22 | Week 4 | #3 FA-151782 | 6- Cylinder Full/Empty | Good | working good
2025-01-22 | Week 4 | #3 FA-151782 | 3- SKA-PAK Cylinder | Good | working good
2025-01-22 | Week 4 | #3 FA-151782 | Valve | Good | working good
2025-01-22 | Week 4 | #3 FA-151782 | Cylinder Pressure Gauge | Good | working good
2025-01-22 | Week 4 | #3 FA-151782 | 3- Face piece | Good | working good
2025-01-22 | Week 4 | #3 FA-151782 | Hook | Good | working good
2025-01-22 | Week 4 | #3 FA-151782 | Leg Support | Good | working good
2025-01-22 | Week 4 | #3 FA-151782 | Tirep | Good | working good
2025-01-22 | Week 4 | #3 FA-151782 | Hydrotest Date | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | Breathing regulator | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | 3- Harnesses Straps | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | 6- Cylinder Full/Empty | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | 3- SKA-PAK Cylinder | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | Valve | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | Cylinder Pressure Gauge | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | 3- Face piece | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | Hook | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | Leg Support | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | Tire | Good | working good
2025-01-29 | Week 5 | #1 FA-151782 | Hydrotest Date | Good | working good
2025-01-29 | Week 5 | #2 FA-151782 | Breathing regulator | Not Available | The equipment operates with high efficiency.
2025-01-29 | Week 5 | #2 FA-151782 | 3- Harnesses Straps | Not Available | Under repair
2025-01-29 | Week 5 | #2 FA-151782 | 6- Cylinder Full/Empty | Not Available | Under repair
2025-01-29 | Week 5 | #2 FA-151782 | 3- SKA-PAK Cylinder | Not Available | Under repair
2025-01-29 | Week 5 | #2 FA-151782 | Valve | Not Available | Under repair
2025-01-29 | Week 5 | #2 FA-151782 | Cylinder Pressure Gauge | Not Available | Under repair
2025-01-29 | Week 5 | #2 FA-151782 | 3- Face piece | Not Available | Under repair
2025-01-29 | Week 5 | #2 FA-151782 | Hook | Not Available | Under repair
2025-01-29 | Week 5 | #2 FA-151782 | Leg Support | Not Available | Under repair
2025-01-29 | Week 5 | #2 FA-151782 | Tire | Not Available | Under repair
2025-01-29 | Week 5 | #2 FA-151782 | Hydrotest Date | Not Available | Under repair
2025-01-29 | Week 5 | #3 FA-151782 | Breathing regulator | Good | working good
2025-01-29 | Week 5 | #3 FA-151782 | 3- Harnesses Straps | Good | working good
2025-01-29 | Week 5 | #3 FA-151782 | 6- Cylinder Full/Empty | Good | working good
2025-01-29 | Week 5 | #3 FA-151782 | 3- SKA-PAK Cylinder | Good | working good
2025-01-29 | Week 5 | #3 FA-151782 | Valve | Good | working good
2025-01-29 | Week 5 | #3 FA-151782 | Cylinder Pressure Gauge | Good | working good
2025-01-29 | Week 5 | #3 FA-151782 | 3- Face piece | Good | working good
2025-01-29 | Week 5 | #3 FA-151782 | Hook | Good | working good
2025-01-29 | Week 5 | #3 FA-151782 | Leg Support | Good | working good
2025-01-29 | Week 5 | #3 FA-151782 | Tirep | Good | working good
2025-01-29 | Week 5 | #3 FA-151782 | Hydrotest Date | Good | working good

## Emergency trailer.
Shedgum Gas Plant Metals Unit Emergency trailer
NAME | SIZE | QTY | REQUIRED | CONDITION | REMARKS
GASKET | ½” x 150 | 3 | 3 | Good | Gasket
GASKET | ¾” x 150 | 4 | 4 | Good
GASKET | 1” x 150 | 4 | 4 | Good
GASKET | 1” x 300 | 4 | 4 | Good
GASKET | 1 ½” x 300/600 | 4 | 4 | Good
GASKET | 2” x 150 | 4 | 4 | Good
GASKET | 2x 300/600 | 4 | 4 | Good
GASKET | 2 ½” x150 | 4 | 4 | Good
GASKET | 3” x 150 | 3 | 3 | Good
GASKET | 3” x 300/600 | 3 | 3 | Good
GASKET | 4” x 300 | 3 | 3 | Good
GASKET | 4” x 150 | 1 | 1 | Good
GASKET | 5” x 300 | 3 | 3 | Good
GASKET | 175 x 50x3mm | 2 | 2 | Good
GASKET | 6” x 150 | 3 | 3 | Good
GASKET | 6” x 300 | 3 | 3 | Good
GASKET | 8” x 150 | 4 | 4 | Good
GASKET | 8” x 300 | 3 | 3 | Good
GASKET | 10” x 150 | 3 | 3 | Good
GASKET | 10” x 300 | 3 | 3 | Good
GASKET | 12” x 150 | 3 | 3 | Good
GASKET | 12” x 300 | 2 | 2 | Good
GASKET | 14” x 150 | 3 | 3 | Good
GASKET | 14” x 600 | 3 | 3 | Good
GASKET | 16” x 150 | 3 | 3 | Good
GASKET | 16”x 300 | 3 | 3 | Good
GASKET | 18” x 150 | 3 | 3 | Good
GASKET | 18” x 300 | 2 | 2 | Good
GASKET | 20” x 150 | 3 | 3 | Good
GASKET | 20” x 300 | 2 | 2 | Good
GASKET | 24” x 300 | 3 | 3 | Good
GASKET | 26” x 300 | 3 | 3 | Good
GASKET | 30” x 150 | 2 | 2 | Good
GASKET | 32” x 300 | 3 | 3 | Good
GASKET | 36” x 150 | 2 | 2 | Good
GASKET | 36” x 300 | 2 | 2 | Good
GASKET | 40” x 150 | 3 | 3 | Good
GASKET | 48” X 300 | 2 | 2 | Good
GASKET | 54” x 150 | 3 | 3 | Good
GASKET | 60” x 150 | 1 | 1 | Good
Boiler maker | 2” X150 | 1 | 1 | Good | Boiler maker
Boiler maker | 2” x300 | 1 | 1 | Good
Boiler maker | 3” x150 | 1 | 1 | Good
Boiler maker | 4” X150 | 1 | 1 | Good
Boiler maker | 4” x300 | 1 | 1 | Good
Boiler maker | 6” x150 | 1 | 1 | Good
Boiler maker | 10” X150 | 1 | 1 | Good
Bolt | 5/8” | 12 | 12 | Good | Bolt
Bolt | 7/8” | 8 | 8 | Good
Bolt | 1 1/8” | 8 | 8 | Good
Bolt | 1” | 16 | 16 | Good
Bolt | 5/8” | 8 | 8 | Good
Bolt | 7/8” | 7 | 7 | Good
Bolt | 5/8” | 19 | 19 | Good
Bolt | ½” | 8 | 8 | Good
Bolt | 5/8” | 14 | 14 | Good
Bolt | 1” | 13 | 13 | Good
Bolt | 1 ½” | 7 | 7 | Good
Bolt | 1 7/8” | 8 | 8 | Good
Bolt | 1 ¼” | 8 | 8 | Good
Bolt | 1 ¼” | 6 | 6 | Good
Bolt | 1 1/12” | 8 | 8 | Good
Bolt | 1 1/8” | 8 | 8 | Good
Bolt | 1 1/8” | 6 | 6 | Good
Plug screw Bolt | N/A | 6 | 6 | Good
Bolt Machine | 1” | 6 | 6 | Good
Bolt (SS) | 5/8” | 22 | 22 | Good
Slip blind | 3” X150 | 1 | 1 | Good | Slip
Slip blind | 10” X150 | 1 | 1 | Good
Slip blind | 3” X300 | 2 | 2 | Good
C-Clamp | 6” | 2 | 2 | Good | Clamp
C-Clamp | 4” | 1 | 1 | Good
C-Clamp | 8” | 1 | 1 | Good
Cylinder oxygen | N/A | 1 | 1 | Good | Cylinder
Cylinder acetylene | N/A | 1 | 1 | Good
Combination Wrench | 15/16” | 2 | 2 | Good | Combination Wrench
Combination Wrench | 1” | 2 | 2 | Good
Combination Wrench | 1 1/16” | 2 | 2 | Good
Combination Wrench | 1 ¼” | 2 | 2 | Good
Combination Wrench | 1 7/16” | 2 | 2 | Good
Combination Wrench | 1 7/8” | 2 | 2 | Good
Combination Wrench | 1 3/8” | 2 | 2 | Good
Combination Wrench | 1 5/16” | 2 | 2 | Good
Combination Wrench | 1 5/8” | 2 | 2 | Good
Combination Wrench | 1 ½” | 2 | 2 | Good
Combination Wrench | 1 11/16” | 2 | 2 | Good
Combination Wrench | 1 13/16” | 2 | 2 | Good
Hammer Wrench | 1 ¼” | 2 | 2 | Good | Hammer Wrench
Hammer Wrench | 1 ½” | 2 | 2 | Good
Hammer Wrench | 1-5/8” | 2 | 2 | Good
Hammer Wrench | 1-1/16” | 2 | 2 | Good
Hammer Wrench | 1 11/16” | 2 | 2 | Good
Hammer Wrench | 2016-01-13 | 2 | 2 | Good
Hammer Wrench | 2” | 2 | 2 | Good
Hammer Wrench | 2-1/8” | 2 | 2 | Good
Hammer Wrench | 2-¼” | 2 | 2 | Good
Hammer Wrench | 2-¾” | 2 | 2 | Good
Hammer Wrench | 2-15/16” | 2 | 2 | Good
Hammer Wrench | 2-3/16” | 2 | 2 | Good
Hammer Wrench | 1-7/16” | 2 | 2 | Good
Hammer Wrench | 2-3/8” | 2 | 2 | Good
Hammer Wrench | 2-5/8” | 2 | 2 | Good
Hammer Wrench | 2-9/16” | 2 | 2 | Good
Impact Wrench | L (1-1/2” Drive) | 1 | 1 | Good | Impact Wrench
Impact Wrench | M (1” Drive) | 1 | 1 | Good
Impact Wrench | S (1” Drive) | 1 | 1 | Good
Impact Wrench Socket | 1-1/8” | 1 | 1 | Good | 1”
Impact Wrench Socket | 1-3/8” | 2 | 2 | Good | Impact Wrench Drive
Impact Wrench Socket | 1-1/16” | 2 | 2 | Good
Impact Wrench Socket | 1-11/16” | 1 | 1 | Good
Impact Wrench Socket | 1-5/8” | 2 | 2 | Good
Impact Wrench Socket | 1-¾” | 2 | 2 | Good
Impact Wrench Socket | 1-13/16” | 2 | 2 | Good
Impact Wrench Socket | 2” | 2 | 2 | Good
Impact Wrench Socket | 2-1/8” | 1 | 1 | Good
Impact Wrench Socket | 2-¼” | 2 | 2 | Good
Impact Wrench Socket | 2-3/8” | 1 | 1 | Good
Impact Wrench Socket | 2-15/16” | 1 | 1 | Good
Impact Wrench Socket | 1-15/16” | 1 | 1 | Good
Impact Wrench Socket | 2-3/16” | 1 | 1 | Good
Impact Wrench Socket | 2-9/16” | 2 | 2 | Good
Impact Wrench Socket | 2-5/16” | 1 | 1 | Good | 1 ½”
Impact Wrench Socket | 2-5/8” | 2 | 2 | Good | Impact Wrench Drive
Impact Wrench Socket | 1-5/8” | 1 | 1 | Good
Impact Wrench Socket | 2” | 2 | 2 | Good
Impact Wrench Socket | 2-15/16” | 1 | 1 | Good
Impact Wrench Socket | 2-3/16” | 1 | 1 | Good
Impact Wrench Socket | 2-7/16” | 1 | 1 | Good
Impact Wrench Socket | 2 ¾” | 2 | 2 | Good
Impact Wrench Socket | 2-7/8” | 2 | 2 | Good
Impact Wrench Socket | 3” | 2 | 2 | Good
Impact Wrench Socket | 3-1/8” | 2 | 2 | Good
Impact Wrench Socket | 1-7/8” | 2 | 2 | Good
Air Hose | 2024-03-04 | 4 | 4 | Good | Hose
Pipe Wrench | 14” | 0 | 1 | Good | Hand Tools
Pipe Wrench | 24” | 2 | 3 | Good
Pipe Wrench | 36” | 0 | 1 | Good
Flat Screw | 10” | 0 | 1 | Good | Hand Tools
Star Screw Drivers | 8” | 0 | 1 | Good
Hole Bari | NA | 1 | 2 | Good
BOLT CUTTER | NA | 0 | 1 | Good
HACK SAW | NA | 0 | 1 | Good
Pipe Cutting | 2” | 0 | 1 | Good
Sledge Hammer | Large | 1 | 2 | Good
WEDGES | NA | 3 | 4 | Good
Adjustable Wrench | 12” | 0 | 1 | Good
Adjustable Wrench | 15” | 0 | 1 | Good
DROP LIGHT 12V | NA | 0 | 1 | Good | Electric
STAND LIGHTS | NA | 0 | 1 | Good | Equipment’s
EXTINCTION CORD | NA | 1 | 2 | Good
COME ALONG 1 TON | NA | 0 | 1 | Good | Lifting
CHIN HOIST 1 ½ TON | NA | 0 | 1 | Good | Equipment’s
SHACKLE | NA | 2 | 2 | Good
NYLON SLING | 1” | 4 | 4 | Good
NYLON SLING | 2” | 1 | 1 | Good
NYLON SLING | 4” | 2 | 2 | Good
NYLON SLING | 6” | 1 | 1 | Good
WIRE SLING | NA | 1 | 1 | Good
NYLON ROPE | NA | 1 | 1 | Good
SAFETY HARNESS | NA | 5 | 5 | Good
RESCUE STRETCHER | NA | 2 | 2 | Good | Rescue
RESCUE BED | NA | 1 | 1 | Good
WELDING GLOVES | Long sleeve | 2 | 2 | Good | Fabrication
FACE SHIELD | NA | 2 | 2 | Good | &
WELDING GLOVES | TIG | 1 | 1 | Good | Welding
WELDING HOOD | NA | 1 | 1 | Good
PENCIL GRINDER | NA | 1 | 1 | Good
CUTTING SET | NA | 1 | 1 | Good
WELDING BLANKET | NA | 1 | 1 | Good
SPARE CUTTING TORCH | NA | 1 | 1 | Good
OXY & ACY HOSE | NA | 1 | 1 | Good
SAFETY HAT | NA | 2 | 2 | Good | PPE
RUBBER GLOVES | NA | 1 | 1 | Good
RUBBER BOOTS | 2024-09-11 | 2 | 2 | Good
DEPOSAL COVERALL | NA | 6 | 6 | Good
Fire Extinguisher | NA | 1 | 1 | Good | Emergency Equipment
Scott Air-Pak | NA | 1 | 1 | Good
Fire Blanket | NA | 1 | 1 | Good
# | Name | ID | Date | Condition | sign
Checked | Abdullah Alaqil | 745207 | 2025-01-01 | Good condition
Approved

## Slip.
Shedgum Gas Plant Metals Unit Slip Blind Report
NO. | Area | Dia | Size /Series | Blind Specification | Corresponding NO. | Date Of Fabrication | Collected by | Recived by | Destroy date | Total Blind | Not Return | Destroy
1 | GT#3 | 1 | 3"*150 | CS, 6 MM thickness | D301A-1 | 2024-11-02 | Raid Sulih | abdullah alaqil |  | 62 | 62 | 0
2 | GT#3 |  | 3"*150 | CS, 6 MM thickness | D301A-2 | 2024-11-02 | Raid Sulih | abdullah alaqil
3 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D301A-3 | 2024-11-02 | Raid Sulih | abdullah alaqil
4 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D301A-4 | 2024-11-02 | Raid Sulih | abdullah alaqil
5 | GT#3 |  | 3"*150 | CS, 6 MM thickness | D301B-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
6 | GT#3 |  | 3"*150 | CS, 6 MM thickness | D301B-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
7 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D301B-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
8 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D301B-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
9 | GT#3 |  | 42"*150 | CS, 6 MM thickness | C301-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
10 | GT#3 |  | 36"*300 | CS, 6 MM thickness | C301-2 | 2024-11-02 | Raid Sulih | abdullah alaqil
11 | GT#3 |  | 3"*300 | CS, 6 MM thickness | C301-3 | 2024-11-02 | Raid Sulih | abdullah alaqil
12 | GT#3 |  | 3"*300 | CS, 6 MM thickness | C301-4 | 2024-11-02 | Raid Sulih | abdullah alaqil
13 | GT#3 |  | 2"*300 | CS, 6 MM thickness | C301-5 | 2024-11-02 | Raid Sulih | abdullah alaqil
14 | GT#3 |  | 2"*300 | CS, 6 MM thickness | C301-6 | 2024-11-02 | Raid Sulih | abdullah alaqil
15 | GT#3 |  | 2"*300 | CS, 6 MM thickness | C301-7 | 2024-11-02 | Raid Sulih | abdullah alaqil
16 | GT#3 |  | 2"*300 | CS, 6 MM thickness | D302-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
17 | GT#3 |  | 2"*300 | CS, 6 MM thickness | D302-2 | 2024-11-02 | Raid Sulih | abdullah alaqil
18 | GT#3 |  | 2"*300 | CS, 6 MM thickness | D302-3 | 2024-11-02 | Raid Sulih | abdullah alaqil
19 | GT#3 |  | 2"*300 | CS, 6 MM thickness | D302-4 | 2024-11-02 | Raid Sulih | abdullah alaqil
20 | GT#3 |  | 48"*300 | CS, 6 MM thickness | C302-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
21 | GT#3 |  | 6"*150 | CS, 6 MM thickness | C302-2 | 2024-11-02 | Raid Sulih | abdullah alaqil
22 | GT#3 |  | 6"*150 | CS, 6 MM thickness | C302-3 | 2024-11-02 | Raid Sulih | abdullah alaqil
23 | GT#3 |  | 2"*150 | CS, 6 MM thickness | C302-4 | 2024-11-02 | Raid Sulih | abdullah alaqil
24 | GT#3 |  | 4"*150 | CS, 6 MM thickness | D303-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
25 | GT#3 |  | 4"*150 | CS, 6 MM thickness | D303-2 | 2024-11-02 | Raid Sulih | abdullah alaqil
26 | GT#3 |  | 36"*150 | CS, 6 MM thickness | D303-3 | 2024-11-02 | Raid Sulih | abdullah alaqil
27 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D303-4 | 2024-11-02 | Raid Sulih | abdullah alaqil
28 | GT#3 |  | 12"*150 | CS, 6 MM thickness | E305-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
29 | GT#3 |  | 8"*150 | CS, 6 MM thickness | E305-2 | 2024-11-02 | Raid Sulih | abdullah alaqil
30 | GT#3 |  | 8"*150 | CS, 6 MM thickness | E305-3 | 2024-11-02 | Raid Sulih | abdullah alaqil
31 | GT#3 |  | 8"*150 | CS, 6 MM thickness | E305-4 | 2024-11-02 | Raid Sulih | abdullah alaqil
32 | GT#3 |  | 2"*150 | CS, 6 MM thickness | E305-5 | 2024-11-02 | Raid Sulih | abdullah alaqil
33 | GT#3 |  | 2"*300 | CS, 6 MM thickness | E305-6 | 2024-11-02 | Raid Sulih | abdullah alaqil
34 | GT#3 |  | 1"*300 | CS, 6 MM thickness | E305-7 | 2024-11-02 | Raid Sulih | abdullah alaqil
35 | GT#3 |  | 2"*300 | CS, 6 MM thickness | E305-8 | 2024-11-02 | Raid Sulih | abdullah alaqil
36 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D311A/B-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
37 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D311A/B-2 | 2024-11-02 | Raid Sulih | abdullah alaqil
38 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D311A/B-3 | 2024-11-02 | Raid Sulih | abdullah alaqil
39 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D311A/B-4 | 2024-11-02 | Raid Sulih | abdullah alaqil
40 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D311A/B-5 | 2024-11-02 | Raid Sulih | abdullah alaqil
41 | GT#3 |  | 2"*150 | CS, 6 MM thickness | D311A/B-6 | 2024-11-02 | Raid Sulih | abdullah alaqil
42 | GT#3 |  | 1.5"*300 | CS, 6 MM thickness | E301-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
43 | GT#3 |  | 1"*300 | CS, 6 MM thickness | E301A-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
44 | GT#3 |  | 1"*44 | CS, 6 MM thickness | E301B-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
45 | GT#3 |  | 8"*300 | CS, 6 MM thickness | D304-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
46 | GT#3 |  | 4"*300 | CS, 6 MM thickness | D304-2 | 2024-11-02 | Raid Sulih | abdullah alaqil
47 | GT#3 |  | 2"*300 | CS, 6 MM thickness | D304-3 | 2024-11-02 | Raid Sulih | abdullah alaqil
48 | GT#3 |  | 8"*300 | CS, 6 MM thickness | D304-4 | 2024-11-02 | Raid Sulih | abdullah alaqil
49 | GT#3 |  | 8"*300 | CS, 6 MM thickness | D304-5 | 2024-11-02 | Raid Sulih | abdullah alaqil
50 | GT#3 |  | 3"*300 | CS, 6 MM thickness | D304-6 | 2024-11-02 | Raid Sulih | abdullah alaqil
51 | GT#3 |  | 3"*300 | CS, 6 MM thickness | D304-7 | 2024-11-02 | Raid Sulih | abdullah alaqil
52 | GT#3 |  | 6"*300 | CS, 6 MM thickness | D304-8 | 2024-11-02 | Raid Sulih | abdullah alaqil
53 | GT#3 |  | 2"*300 | CS, 6 MM thickness | D304-9 | 2024-11-02 | Raid Sulih | abdullah alaqil
54 | GT#3 |  | 3"*300 | CS, 6 MM thickness | D304-10 | 2024-11-02 | Raid Sulih | abdullah alaqil
55 | GT#3 |  | 1.5"*150 | CS, 6 MM thickness | D304-11 | 2024-11-02 | Raid Sulih | abdullah alaqil
56 | GT#3 |  | 3"*150 | CS, 6 MM thickness | D304-12 | 2024-11-02 | Raid Sulih | abdullah alaqil
57 | GT#3 |  | 4"*300 | CS, 6 MM thickness | D304-13 | 2024-11-02 | Raid Sulih | abdullah alaqil
58 | GT#3 |  | 2"*300 | CS, 6 MM thickness | D304-14 | 2024-11-02 | Raid Sulih | abdullah alaqil
59 | GT#3 |  | 8"*300 | CS, 6 MM thickness | D304-15 | 2024-11-02 | Raid Sulih | abdullah alaqil
60 | GT#3 |  | 8"*300 | CS, 6 MM thickness | D304-16 | 2024-11-02 | Raid Sulih | abdullah alaqil
61 | GT#3 |  | 1.5"*300 | CS, 6 MM thickness | D314-1 | 2024-11-02 | Raid Sulih | abdullah alaqil
63 | GT#3 |  | 2"*300 | CS, 6 MM thickness | D314-3 | 2024-11-02 | Raid Sulih | abdullah alaqil
64 | GT#3 |  | 1"*150 | CS, 6 MM thickness | D306-1 | 2024-11-02 | Raid Sulih | abdullah alaqil

## Audit.
Shedgum Gas Plant Metals Unit Inspection Audit Items
# | Location | Audit item | Observations | Status
1 | Metal Yard | Materials | Leftover material in the reclamation yard | In Progress
2 | Metal Yard | Arrangment | Improper storage of plates in the rack | Completed
3 | Metal Yard | Arrangment | Stainless Steel piping are stored in non-SS rack | Completed
4 | Metal Yard | Project | Exhaust Fans are not installed yet except 2 for proper ventilation | Completed
5 | Metal Yard | Arrangment | insufficient protective clothing for welders protective clothing | Completed
6 | Welding Shop | Arrangment | SS 308 rods are stored in SS 309 shelf | Completed
7 | Hydro test Area | Arrangment | 2.5mm 6010 CS is stored in 2.4mm electrode. | Completed
8 | Hydro test Area | MTC | 2 of fume extractor were found with very low vacuum pressure | In Progress
9 | Welding Shop | Inspection | Faded ASME stamp | Pending
10 | Welding Shop | Arrangment | Piping are stored directly to the ground | Completed
11 | Welding Shop | Documents | Provide the weld maps for all welding activity | In Progress
12 | Welding Shop | Documents | Update the welder performance log | Completed
13 | Welding Shop | Documents | Provide electrode log to track the used number of electrodes. | Completed
14 | Welding Shop | Arrangment | Maintain the weld identification (weld number & welder symbol) | Completed
15 | Welding Shop | MTC | Maintain the color coding of the Metal Shop. | In Progress
16 | Welding Shop | Arrangment | Piping and its components shall be placed on clean mounds, sand bags or sleepers. | Completed
17 | Welding Shop | Arrangment | Prevent mix up of materials | Completed
18 | Welding Shop | Documents | Provide the revalidation/ calibration documents for all welding machines/ ovens. | Completed
19 | Welding Shop | Documents | Recertify the expired welder certification. | In Progress

## On going
Shedgum Gas Plant Metals Unit On Going Activity
# | Area | Equipmnt | Describtion | Update | Priorty | Status | Remark
1 | GT#2 | D-201 A Feed Filter North | Fabricate New bridle | Pre-Fab acompleted,replace unioin to flange in progress | High | In Progress
2 | GT#2 | D-201 A Feed Filter South | Fabricate New bridle |  | High | completed | Track to load to shop
3 | GT#2 | D-201 B Feed Filter North | Fabricate New bridle |  | High | Completed | Machining requirment
4 | GT#2 | D-201 B Feed Filter South | Fabricate New bridle |  | High | Completed | Hydrotest requirment
5 | GT#2 | D-201 Flash Drum | Fabricate New bridle |  | Medium | completed | Rquist materials Union 1 1/2"
6 | GT#2 | C-201 Contactor Drum T. | Fabricate New bridle |  | Medium | completed | Rquist materials flange and Elbow
7 | GT#2 | C-201 Contactor Drum M. | Fabricate New bridle |  | Medium | completed | Rquist materials 1 1/2" reducer
8 | GT#2 | C-201 Contactor Drum B. | Fabricate New bridle |  | Medium | In Progress
9 | GT#2 | C-202 Striper | Fabricate New bridle |  | Medium | completed | pre-pration completed
10 | GT#2 | D-203 Reflex Drum | Fabricate New bridle |  | Medium | completed | pre-pration completed

## Certificate.
Shedgum Gas Plant Metals Unit Unit Certification
Certificate Type | value
Forklift Driver 18 | 2
Forklift Driver 2.5 | 3
Rigger | 4
Work Permit Recipient | 19
Torqueing | 5
Welder | 10
Fabrecator | 8